Draft Report on the Status of Categorical Program Monitoring for Economic Impact Aide (Title III)

July 2010

Ted Herr

| Guidelines | Compliance issue | Compliance efforts |
| --- | --- | --- |
| I-EL 1. The LEA outreach to parents of English learners includes the following actions: - The LEA sends notice of and holds regular meetings for the purpose of formulating and responding to the parents’ recommendations. (20 USC 7012[e][2]) - The LEA informs the parents how they can be involved in the education of their children and be active participants in assisting their children to: - Attain English proficiency - Achieve at high levels in core academic subjects Meet challenging state academic standards expected of all students (20 USC 7012[e][1]) | This outreach was not conducted at Woodcreek High School (WHS). | April 2010 – Emails sent to non-compliant schools stating the issues and offered assistance and requesting a phone conversation. WHS will be approached again when returning from summer vacation. If the issue is not corrected, it will be escalated in the district. |
| I-EL 2. A school site with 21 or more English learners has a functioning EL Advisory Committee (ELAC) that meets the following requirements: | Woodcreek High and Oakmont High did not hold required English Learner Advisory Committee (ELAC) meetings this last year (2009-2010). Antelope High scheduled the meetings but parents only attended the first one. Roseville High was very successful with ELAC meetings. No other school is required to hold ELAC meetings. (All schools with 21 or more English Learners must hold ELAC meetings. | April 2010 – Emails sent to non-compliant schools stating the issues and offered assistance and requesting a phone conversation. WHS and OHS did not respond. The OHS administration team member responsible has been contacted at her office and apprised of the situation. WHS and OHS will be approached again when returning from summer vacation. If the issue is not corrected, it will be escalated in the district. |
| I-EL 3. A LEA with 51 or more English learners has a functioning DELAC or a subcommittee of an existing district committee in which at least 51 percent of the members are parents (not employed by the district) of English learners. | The DELAC did not meet for most of 2009-2010. | DELAC meetings were held in April and May of 2009. Parents were informed of the non-compliance and plans were made to correct the issue. Monthly DELAC meetings have been scheduled for 2010-2011. |
| II-EL 5 The LEA properly identifies, assesses, and reports all students who have a primary language other than English. 5.3 Within 90 calendar days of initial enrollment, each English learner is assessed for primary language proficiency. (EC 52164.1[c]) | Assessing students for primary language proficiency has only been completed sporadically in the district. | The process will be expanded to include - Language assessment tests in the home language where available, and - Informal language surveys, for less common home languages. |
| II-EL 5 The LEA properly identifies, assesses, and reports all students who have a primary language other than English. The district uses transcripts from schools in their home language for assessment. The method works well when transcripts are available, however, when transcripts are not available, the students are not 5.5 (For school districts receiving Title III funds) Within 30 calendar days after the beginning of the school year (or during the school year, within two weeks of child being placed in program), parents/guardians of English learners are notified of: - Their child’s initial English language and primary language proficiency level - How such level was assessed - Their child’s language designation - Descriptions of program options - Program placement - Exit criteria - For English learners with a disability [with an individualized education program (IEP)], how such program will meet the objectives of the IEP. The expected rate of graduation from secondary school if funds under this part are used for children in secondary school. (20 USC 6312, 7012) assessed. | This notification has not been taking place. | The English Learner Coordinator will use the Aeries database to download the pertinent information. An automated letter will be generated and sent to parents. Notifications will be tracked in a database. |
| 5.6 (For school districts receiving Title III funds) Parents/guardians of English learners are informed annually, not later than 30 days after the beginning of the school year, of: - Their child’s English proficiency level - How such level was assessed - The status of the child’s academic achievement - Their child’s language designation - Descriptions of program options - Program placement - Exit criteria - For English learners with a disability (on IEPs), how such program will meet the objectives of the IEP The expected rate of graduation from secondary school if funds under this part are used for children in secondary school (20 USC 6312, 7012) | This requirement parallels section 5.5. This notification has not been taking place. | The English Learner Coordinator will use the Aeries database to download the pertinent information. An automated letter will be generated and sent to parents. Notifications will be tracked in a database. |
| II-EL 5 The LEA properly identifies, assesses, and reports all students who have a primary language other than English. 5.7 Each English learner is annually assessed for English language development and academic progress. (5 CCR 11306) | English Learners are assessed annually for Englihs language development. The students are not assessed annually for academic progress. | The English Learner coordinator will develop a systematic method for reviewing and assessing the academic progress of all English Learners. |
| II-EL 5 The LEA properly identifies, assesses, and reports all students who have a primary language other than English. 5.9 Each English learner with disabilities is assessed for English language development using accommodations, modifications, or alternate assessments for the CELDT if specified in the pupil’s IEP or 504 Plan. (5 CCR 11516) | Studnets with disabilities have been generally tested using the CELDT without any modifications or accommodations. | The English Learner Coordinator will work with the director of Special Education to create a process for noting modifications and accommodations in the students IEP or 504 plan and making the information accessible to the EL Coordinator. The EL Coordinator and the Director of Special Education will determine the most appropriate means for testing each student affected and will coordinate the testing of those students. |
| II-EL 7. (Previously II-CP 5 in 2008-09) For all programs funded through the Consolidated Application including programs for English learners and EIA-LEP and Title III and operated at the school, the school site council (SSC) annually develops, reviews, updates, and approves the Single Plan for Student Achievement (SPSA), including proposed expenditures. The SPSA consolidates all plans required by these programs and contains (EC 64001[f],[g],[h]): - Analysis of academic performance data to determine student needs. - School goals to meet the identified academic needs of students. - Activities to reach school goals that improve the academic performance of students. - Expenditures of funds allocated to the school through the Consolidated Application. The means of annually evaluating the progress of programs toward accomplishing the goals, including determining whether the needs of all children have been met by the strategies used, particularly the needs of low-achieving students and those at risk of not meeting state academic content standards. (20 USC 6314[b][1][2], 6315[c][2], EC 64001[f]) |  |  |
| II-EL 7. (Previously II-CP 5 in 2008-09) For all programs funded through the Consolidated Application including programs for English learners and EIA-LEP and Title III and operated at the school, the school site council (SSC) annually develops, reviews, updates, and approves the Single Plan for Student Achievement (SPSA), including proposed expenditures. The SPSA consolidates all plans required by these programs and contains (EC 64001[f],[g],[h]): The SSC annually considers whether or not it wishes the local school to participate in the school-based coordination program (SBCP) and that decision is indicated in the SPSA. (EC 52852.5 (b)) |  |  |
| III-EL 10. Adequate general fund resources are used to provide each English learner with learning opportunities in an appropriate program, including English language development, and the rest of the core curriculum. The provision of such services is not contingent on the receipt of state or federal categorical aid funds. (20 USC 1703[f]; Castañeda v. Pickard [5th Cir. 1981] 648 F.2d 989, 1010, 1012-1013) | Long-term English Learners have been systematically excluded from direct services. | The district recognizes the problem and has taken staps to address it. 11 staff members representing the district, Roseville High School and Antelope High School attended training provided by Dr. Laurie Olsen. Oakmont High School has been operating a CAHSEE ELA preparation course for addressing a part of the issue. Roseville High School has created an Academic Language Proficiency class for 2010-2011 to partially address the issue. The English Learner Coordinator will coordinate educational efforts within the district about the issue, as well as recommend specific approaches to addressing the issue at each site. |
| III-EL 11. (Previously III-CP 9 in 2008-09) The LEA disburses categorical funds including EIA-LEP in accordance with the approved Consolidated Application. (EC 62002, 64000[b], [c], 64001[g]) For programs funded by Economic Impact Aid (EIA), the LEA uses no less than 85 percent of those apportionments at school sites for direct services to students. | The district uses less than 85% of the funds on direct services. The district spends approximately 75% of its apportionments on programs for English Learners. The balanced is carried over in reserves. | The English Learner Coordinator will create a plan to expand services to English Learners. |
| IV-EL 14. The LEA implements a process and criteria to determine the effectiveness of programs for English learners, including: - A way to demonstrate that the programs for English learners produce, within a reasonable period of time: - English language proficiency comparable to that of average native speakers of English in the district . Academic results indicating that English learners are achieving and sustaining parity of academic achievement with students who entered the district’s school system already proficient in English | The district’s English Language Development program meets the AMAO’s on an annual basis. The district has identified a sub-group of English Learners (long-term English Learners) who are persistently failing to move forward and have severe credit deficiencies. | The district recognizes the problem and has taken staps to address it. 11 staff members representing the district, Roseville High School and Antelope High School attended training provided by Dr. Laurie Olsen. Oakmont High School has been operating a CAHSEE ELA preparation course for addressing a part of the issue. Roseville High School has created an Academic Language Proficiency class for 2010-2011 to partially address the issue. The English Learner Coordinator will coordinate educational efforts within the district about the issue, as well as recommend specific approaches to addressing the issue at each site. |
| IV-EL 15. The LEA reclassifies a pupil from EL to proficient in English by using a process and criteria that include, but are not limited to: - The LEA maintains in the pupil’s permanent record documentation of the following: - Language and academic performance assessments - Participants in the reclassification process | The district’s adopted reclassification procedure contains one criteria that is possibly not supported in law (length of tiem with English instruction). The process has not been handled correctly on a consistent basis. The participants in the reclassification process have not selected and consulted on a consistent basis. The district does not maintain documentation in the students’ permanent records of the participants in the process. | The English Learner Coordinator will oversee the process to re-establish consistency. The district will review the process for compliance with the guidelines. |
| V-EL 16. Teachers assigned to provide English language development or access to core curriculum instruction for English learners are appropriately authorized or are actively in training for an appropriate EL authorization. 16.1 On documentation of a local shortage of qualified teachers to provide such instruction, the district has adopted and is implementing measures by which it plans to remedy the shortage. | The district does not have all teachers authorized for EL services and probably violates the law in several content areas. (Violations occured in the 2008-2009 school year that were not addressed. Research is needed to determine if violations occurred in the 2009-2010 school year. | The district is aware of the issue and has provided extensive support for teachers seeking authorization. A number of teachers have not complied with the district’s directives for compliance. The issue will be reviewed in the Fall of 2010. Only duly authorized teachers are hired as new staff in the district or are hired conditionally on completing the authorization. |
| V-EL 17. The LEA provides high-quality professional development to classroom teachers, principals, administrators, and other school or community-based personnel that is: (d ) Of sufficient intensity and duration (which shall not include activities such as one-day or short-term workshops and conferences) to have a positive and lasting impact on the teacher’s performance in the classroom. (20 USC 6825[c][2][D]) (Castañeda v. Pickard [5th Cir. 1981] 648 F.2d 989, 1009-1011) | The district has provided sufficient professional development to |  |